Guía2. Desarrollo Proyecto APT

Asignatura Capstone

1. Resumen avance Proyecto APT

Complete the fields below with the requested information.

| APT project progress summary | Cutoff date: 5 October 2026. Development started on Monday 24 August and has run in parallel with the documentation: Sergio on FastAPI and PostgreSQL, Julio on the React screens, and Felipe on the board, the dailies and testing. Sprint 1 (24 Aug – 4 Sep), closed. Email and password login with JWT, user creation with roles, inventory by serial number and QR, status change, search, and the first work order. The front end already consumes those endpoints locally. Sprint 2 (7 – 17 Sep), closed. The technician records the work order with a photo and a canvas signature. Removed equipment returns to the warehouse (transfer and status change). A critical-stock alert is in place. 18 September was not worked: it is a public holiday. Sprint 3 (21 Sep – 2 Oct), closed. Payment order against Flow in sandbox, falling back to a mock if the gateway does not respond. Webhook tested with ngrok. Simulated DTE in PDF. The DTE XML slipped inside the sprint, but it closed on 2 October. Sprint 4 started today. Planning is done. Sergio started the dashboard SQL views; Julio does not yet have stable charts. The sale of the recovered monitor (HU-BILL-06) is planned for 8–15 October and has not started. Final Docker and end-to-end tests are set for 13–16, because the 12th is a public holiday. |
| --- | --- |
| Objetives | The goal did not change: serial-level inventory traceability and less time to collect payment in the field. The scope was made more precise. Login is by email, not by national ID. The sale of the asset that returns to the warehouse (recovered monitor) was added as a Sprint 4 story, because charging for the service did not cover that sale. |
| Methodology | Scrum remains, with two-week sprints and a reference of 26 points. Sprint 4 went to 31 points when the recovered-asset sale was added. The real cadence was Monday, Wednesday and Friday, not a daily every day. Code is integrated on GitHub through pull requests. Flow and the tax authority were tested with sandbox and mock, not against production. |
| Evidence of progress | Evidence for this cutoff: Gantt chart as of 5 October, backlog with stories and acceptance criteria, log of 18 dailies (sprints 1 to 3) and the retrospectives of those three cycles. In code: login, inventory with QR, work order with photo and signature, and the payment screen with mock, running in local Docker. Quality was guarded with a Definition of Ready before a story entered the sprint and a Definition of Done on the way out: a basic test, review by another member, and the service running in a container. The dashboard is not fully tested: that starts this week. |

2. Work-plan monitoring

Review the work plan, especially the progress status and adjustments columns.

| Work plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activities | Resources | Duration | Owner | Notes | Progress status | Adjustments |
| Software development | Email login, JWT and roles | FastAPI, PostgreSQL, React, Tailwind | 24–28 Aug (4 days) | Sergio Bravo and Julio Mena | CORS between React and FastAPI on the first Wednesday. Middleware was enabled. | Completed | Login identifier changed from national ID to email. |
| Software development | Inventory by serial, QR, statuses and search | PostgreSQL, qrcode.react, React | 27 Aug – 3 Sep | Sergio Bravo and Julio Mena | The QR library did not render on React 18. A compatible version was pinned. | Completed | No scope change. |
| Software development | Create and assign the first work order | FastAPI, React, GitHub Projects | 2–4 Sep | Sergio Bravo and Julio Mena | It depended on login and asset registration. Tested with a trial technician. | Completed | Brought forward to Sprint 1 so the work order would not wait until Sprint 2. |
| Software development | Field evidence: photo and signature | React canvas, multipart upload, FastAPI | 7–15 Sep | Julio Mena and Sergio Bravo | HD photos exceeded 2 MB. The limit was raised to 10 MB and images were compressed on the front end. A clear-signature button was missing. | Completed | A loading spinner was added. Closed on the 17th, not the 18th (public holiday). |
| Software development | Return to warehouse and critical stock | PostgreSQL, React | 11–17 Sep | Sergio Bravo and Julio Mena | Equipment removed on the work order had to return to the warehouse with a status. Without that, there is no later sale. | Completed | RECOVERED status, in addition to AVAILABLE and DECOMMISSIONED. |
| Software development | Flow/mock payment, webhook and simulated DTE | Flow sandbox, ngrok, dicttoxml, PDF | 21 Sep – 2 Oct | Sergio Bravo and Julio Mena | The webhook did not reach localhost. The DTE XML took longer than estimated. | Completed | If Flow does not respond, the payment is marked SIMULATED_APPROVED. The real tax authority is not used. |
| Scrum management and QA | Board, dailies, tests and retrospectives | GitHub Projects, backlog and daily spreadsheets | 24 Aug – 5 Oct, and ongoing | Felipe Madrid | Documentation lagged the code on some days. Dailies were held Mon/Wed/Fri. | In progress | No ceremony was dropped. The everyday daily was adjusted to three per week. |
| Software development | KPI dashboard (SQL views and charts) | PostgreSQL, Recharts, React | 5–14 Oct | Sergio Bravo and Julio Mena | Grouped queries are slow. An index is missing on work-order date and asset status. | In progress | Started today. Charts are not stable yet. |
| Software development | Sale of recovered monitor and payment | Inventory, Flow/mock, DTE already built | 8–15 Oct | Sergio Bravo and Julio Mena | Depends on the asset being in the warehouse (Sprint 2) and on payment already existing (Sprint 3). | Not started | New story HU-BILL-06. It was not in the initial backlog. |
| Quality and infrastructure | Final Docker Compose, Swagger and E2E test | Docker, FastAPI, React | 13–16 Oct | Sergio Bravo, Julio Mena and Felipe Madrid | 12 October is a public holiday. In an earlier trial, port 8000 collided. | Not started | The week was moved to 13–16. |

3. Adjustments from monitoring

Go deeper on the work-plan notes. Review the planned activities and state what helped or hindered execution. Explain how obstacles were, or will be, handled. Then state the adjustments made to the work plan from this analysis.

Factors that have helped and/or hindered the work plan: It helped to split the scope into small stories and to have the front end consuming the API in the same week as the endpoint. Marco, as product owner, answered quickly when the signature and the simulated receipt were tested. The Flow mock kept Sprint 3 from stopping when the sandbox failed. CORS in the first sprint, the photo size limit and the DTE XML, which ran over the estimate, got in the way. The sprint was not stopped: it was logged in the daily, adjusted in the same cycle and closed with a manual test. The 18 September and 12 October holidays forced Sprint 2 to close on the 17th and the last week to move to 13–16.

Adjusted or removed activities: No pillar was removed. The access identifier was adjusted (email instead of national ID), status change, search and the first work order were brought into Sprint 1, and the sale of the monitor that stays in the warehouse was added. That sale was not in the first backlog: it appears now because replacements leave recovered equipment that the company sells. The every-day daily was reduced to three per week. That was enough to surface blockers without inventing meetings.

Activities not started or behind schedule: Not started, and not behind the Gantt: sale of the recovered monitor (starts 8 October) and Docker/E2E close (starts on the 13th). The dashboard is in progress as of today; the charts cannot be shown yet. If the SQL views stay slow, Sergio adds the indexes this week and Julio does not wait for perfect data to lay out the board with test data. The real slip already absorbed was the DTE XML, inside Sprint 3. It closed on 2 October, the review date. It does not carry into Sprint 4.