Guía3. Informe final Proyecto APT

Asignatura Capstone

1. Final APT project report

The aim of this report is to describe the most relevant aspects of your APT project. You should explain the decisions made along the way. Complete the fields below. They cover the summary of the APT project and its main results.

| Project name | MARCOM — Technology and inventory management platform, for Sociedad de Instalaciones Marcom Compañía Limitada. |
| --- | --- |
| Area(s) of practice | Software development (back end and front end), IT project management and quality assurance. The case sits in the operation of a technology installation and maintenance company. |
| Competencies | Analysis of a business problem and translation into requirements. Building a web solution with an API, a database and an interface. Teamwork with Scrum, version control and testing. Integration with an external service using a fallback mechanism. |

| Final report contents |  |
| --- | --- |
| 1. Relevance of the APT project | - Marcom installs and maintains equipment in service stations and stores. Stock was kept in spreadsheets, the field work order stayed on paper or on the technician’s phone, and payment was late because the evidence and the invoice did not come from the same record. Replaced equipment (for example a monitor) returned to the warehouse with no clear status, and was later sold outside the system. - The case is in the company’s operation in the Metropolitan Region. It affects whoever runs the warehouse, the field technician, whoever collects payment, and the client who receives the service. It is not a single-site problem: it repeats at every branch served. - The contribution in this cycle is a locally usable MVP: inventory by serial and QR, a work order with photo and signature, return of equipment to the warehouse, simulated payment (Flow sandbox or mock) and a simulated tax receipt. The sale of the recovered monitor was included in the close. There was no connection to the real tax authority and no client was charged. |
| 2. Objectives | - General objective: leave a platform that records the asset by serial, the field order with evidence, and payment for the service, without loose spreadsheets. - Specific objectives: authenticate by email and role; register, search and change the asset status; create and close the work order with photo and signature; return removed equipment to the warehouse; charge through Flow or a mock and issue a simulated tax receipt; show basic KPIs for work orders, stock and billing; record the sale of the recovered asset. |
| 3. Methodology | - Scrum was used in four two-week sprints, from 24 August to 16 October 2026. Each sprint had planning, dailies on Monday, Wednesday and Friday, a review and a retrospective. The backlog was estimated in points. A story entered if it met the Definition of Ready and left if it met the Definition of Done: reviewed code, a basic test and the service in a container. - It was appropriate because the scope could be split (access, warehouse, field, payment, dashboard) and the product owner could see an increment every two weeks. A waterfall build would have left payment and evidence until the end, which was exactly the company’s problem. - Stack: React and Tailwind on the front end, FastAPI and PostgreSQL on the back end, Docker to run the environment. Flow and the tax authority were handled with sandbox and mock, not with a tax certification. |
| 4. Development | - Sprint 1 (24 Aug – 4 Sep): email login and JWT, roles, asset registration with QR, statuses, search and the first work order. Front end and back end moved in the same week. - Sprint 2 (7 – 17 Sep): work-order execution with photo and signature, status lookup, warehouse transfer and critical stock. The 18th was not worked because of a public holiday. - Sprint 3 (21 Sep – 2 Oct): payment order, Flow sandbox with fallback to mock, test webhook, simulated tax receipt and agreement documents. - Sprint 4 (5 – 16 Oct): dashboard, sale of the recovered monitor, and close with Docker and an end-to-end test. As of 5 October this stage is open: planning was done and the dashboard views started; the sale starts on the 8th and the technical close on the 13th, because the 12th is a public holiday. - Small stories, the payment mock and the product owner’s quick response on the signature and receipt tests helped. CORS in the first sprint, photo size, the tax-receipt XML and two public holidays got in the way. Scope was not cut: login changed from national ID to email, the first work order was brought into Sprint 1, and the recovered-asset sale was added. It was not in the first backlog. |
| 5. Evidence | - To see the process: Gantt chart, backlog with acceptance criteria, daily log, retrospectives for sprints 1 to 3, and the phase 2 progress report. - To see the result: repository with the services, login screens, inventory with QR, work order with signature, payment in simulated mode and, at the Sprint 4 close, the KPI dashboard. Payment and the tax receipt are test artifacts. There is no real tax invoice. |
| 6. Professional interests and outlook | - The project confirmed that I am as interested in coordination and quality as in the screen. I joined as Scrum Master and also supported testing and the order of the documentation, while Sergio held the API and Julio the front end. That matches what I already do on site and in models: leave a traceable process, not only a loose deliverable. - The interest did not change subject; it became more precise. I still want to join software with technical operations (inventory, field work, evidence), not only dashboards. After this cycle I see myself applying the same approach in BIM coordination and in small tools for field teams: version control, a definition of done, and an interface a technician can use without a long training. The recovered-asset sale and the simulated payment showed the limit: integrating an external service without a certificate is not the final product; it is how the team avoids getting blocked. |